## Slide 1
PROJECT SUMMARY
valops-agent
A contained, read-only incident-analysis assistant for one Agave validator on Solana testnet
Plan
v0.5
HLD
v0.5
Codebase
M0 status
Peng Huang · 21 September 2026 · DRAFT for review
Notes: Sources: solana-agave-node-ops-agent-plan-v0.5.md (governs), valops-agent-mvp-hld-v0.5.md, docs/IMPLEMENTATION-NOTES.md, and a test run on 2026-09-21.

## Slide 2
At a glance
M0 is deliberately narrow. The containment layer comes first; the diagnosis workflow is built on top of it
1
Agave testnet validator
one named on-call operator + backup
0
validator write paths
no executor, no approval service in M0
5
supported fault classes
FC-1 … FC-5, each injectable on testnet
3
model providers
Claude (reference) · Codex · Gemini via Antigravity
CONDITIONAL NO-GO
Both documents gate implementation on G0. The M0 code was written ahead of G0 at the owner's request.
It carries no gate weight until G0 approves the delivery package.
Dev suite: 106 tests pass, 14 skipped (they need the pinned runtime or a live provider key).
Next step: close the G0 decisions, then prove the 4 containment properties on real boundaries (G1).
Plan §2.6, §7.2 · README gate status · pytest run 2026-09-21
2

## Slide 3
What M0 is — and what it is not
PRODUCT HYPOTHESIS [H]
For the supported fault classes, an evidence-linked incident report delivered within the latency target lets the on-call operator reach a correct diagnosis faster and with less effort than the agave-watchtower alert alone — at acceptable cost and with no measurable impact on the validator.
M0 IS
A read-only incident-analysis assistant for a named operator
Observes one Agave testnet validator (tiers T0 / T1 only)
Opens an episode, diagnoses with ranked, falsifiable hypotheses
Recommends; an isolated Judge checks every recommendation
Reports to the operator's channel alongside watchtower
Confirms recovery deterministically, then sends a closure report
M0 IS NOT
An autonomous validator operator — it executes nothing
Restarts, upgrades, failover (set-identity), snapshot download
Stake, delegation, commission or withdrawer-key operations
Non-Agave clients, mainnet-beta, or multi-validator fleets
The offline tuning loop or published trust metrics
A claim of zero availability risk (residual load is bounded)
Plan §2.1–§2.6 · HLD §1–§2
3

## Slide 4
Supported fault classes
Each class has a reproducible testnet injection; the injector records the root cause before the operator reads a report
 | Fault class | Injection on testnet | Primary signals
FC-1 | Validator process stopped / unit failed | Stop the systemd unit | unit state, catch-up
FC-2 | Identity balance below floor | Transfer out until below P-02 | identity_balance
FC-3 | Ledger / accounts volume low on headroom | Ballast file below P-04 | host_metrics
FC-4 | Running version ≠ expected | Declare a different expected version | running_version
FC-5 | Telemetry loss (unreachable, slow, stale) | Stop, throttle or partition observer | telemetry probes
Outside FC-1 … FC-5?
It still opens an episode and a report, labelled “outside supported classes”. It counts toward operator burden (Q-5) and cost (Q-6), but not toward diagnosis quality (Q-1) or actionability (Q-2). Telemetry loss never raises, lowers or resolves a validator-health episode: missing data is its own incident (FR-13).
Plan §2.6 · FR-13
4

## Slide 5
Architecture: the model never holds a capability
Four process classes with disjoint credentials; every check re-done by a broker outside the model's process
OPS HOST (no keypairs)
Sentinel + telemetry-health checks
deterministic; opens episodes
CONTROLLER (trusted)
episode runner · CAS transitions · artefact validation · mints scoped tokens · holds no provider key
WORKER (untrusted · bwrap sandbox)
One adapter: Claude SDK │ codex exec │ agy -p │ native loop
One role · one episode · fresh session
No provider key · no fs writes · egress = model broker only
Episode store
5 endpoints · append-only
Policy bundles
immutable · hash-addressed
Verifier — only writer of `resolved`
fork/exec per step
CAPABILITY BROKERS
episode-broker
agent appends only
report-broker
reports + alert sink
observer-broker
allowlist + rate limit
audit-sequencer
sole chain writer
model-broker
sole key holder · limits
UDS +
token
VALIDATOR HOST
Observer daemon (user valops, no keys)
read-only command table by id
concurrency 1 · rate limits · cgroup
local hash chain
agave-validator (user sol) · no executor
External anchor (WORM)
signed chain heads, off-host
Anthropic · OpenAI · Google
per bound configuration only
mTLS
A full worker compromise yields only the tool surface its token already permits, for one episode, until the token expires.
HLD §4.1–§4.3 · Plan §4.2 · N-1/N-2 (5 store endpoints), N-3 (bind-mounted sockets)
5

## Slide 6
One episode, end to end
A fresh session per step; the controller validates each step's artefact before it advances state
1
Sentinel
detects; opens episode, binds bundle
2
Diagnostician
ranked, falsifiable hypotheses
3
Change-planner
recommendation or no-action
4
Proposal-judge
PASS / FAIL, isolated inputs
5
Reporter
report + one alert (AW-2)
6
Operator
acks, acts by hand, scores rubric
7
Verifier
confirms recovery → resolved + closure report
Deterministic
LLM role session
Human
Fail → hand off
Missing artefact, schema failure, budget or retry exhausted, Judge FAIL after retry, provider outage: no action, state handed_off, human alerted.
The agent cannot close
set_state(resolved) doesn't exist on any agent endpoint. Only the verifier resolves, and only from awaiting_operator.
Consensus mode checked
The declared mode is cross-checked against version, feature state and state files. Any disagreement → unknown, and mode-specific advice is refused.
Plan §2.6 AW-1…AW-6, §5.6–§5.11 · HLD §7.2 · N-4, N-5, N-7
6

## Slide 7
v0.5: three providers, one boundary
Runtimes are admitted by conformance tests; in-process controls are defence in depth only
 | Claude | Codex | Gemini via Antigravity
Runtime | Agent SDK (Python) | codex exec | agy -p (headless)
Built-ins removable | Yes | Not documented [U] | Not documented [U]
Endpoint override | To show in W1 [U] | openai_base_url | Not documented [U]
Auth | API key | API key or login | Cached login
Expected admission [H] | Runtime admitted | Runtime if built-ins inert, else native | Native-only likely
Model broker
Sole holder of every provider key
The worker's only network egress
Model allowlist per (episode, role)
Provider-neutral request, token and USD limits
Transcript of record → audit chain
Cost (Q-6) comparable across providers
A runtime that can't be pointed at the broker isn't admitted. The native API adapter (no built-in tools) is the floor for every provider.
Admission profile PC-1 … PC-9: headless and killable · only valops tools reachable · no config discovery · no credential in the worker · inside the bwrap sandbox · MCP over stdio · no phone-home · exact pin · prompt from the bundle only.
Every episode is bound to one configuration. Results are never pooled across configurations, and G2 is granted per configuration.
Plan §5.12 · HLD §5.12, §6.5, §16.1 · D19–D22
7

## Slide 8
How M0 is judged
Safety gates must pass 100%; model-quality gates use frozen fixtures and confidence bounds
Q-1
Diagnosis quality
top-ranked hypothesis correct
Q-2
Actionability
FB-2 ∈ {1,2}; unsafe flags = 0
Q-3
Report latency
episode open → alert, p50 / p95
Q-4
Time vs. watchtower
paired reduction; lower bound > 0
Q-5
Operator burden
alerts/day, false-alarm share
Q-6
Cost
USD per episode and per day
Q-7
Observation impact
local-RPC latency on vs. off
Q-8
Safety
unauthorised executions = 0
Deterministic gates
Containment, policy, sandbox, bundle lifecycle, concurrency, degradation, backup. 100% pass, every run, over P-22 = 20 trials. One failure blocks.
Model-quality gates
Diagnosis, actionability, Judge detection. The lower 95% Wilson bound must clear the target; fixture sets are frozen and hashed; humans adjudicate disputes. Seeded Judge cases: zero misses.
Plan §2.6, §8.1, §13.2–§13.3
8

## Slide 9
Roadmap: staged authorisation
No gate may be skipped or merged. Schedule pressure is not evidence
M0A containment prototype
7-week box · 63 eng-days · 2 engineers
M0B diagnosis workflow
baseline campaign + 28-day run-in
M1 gated actions
testnet T2 → shadow mode → limited autonomy
G0
G1
G2
Provider track (parallel): W1-O, W1-G, W21–W23 · 22 eng-days · PA per configuration
WE ARE HERE
G0 → authorises M0A coding
Delivery package: frozen product definition, M0A decisions closed or defaulted, approved registers, gate classes, charter with named DRIs, governance, runbooks.
G1 → authorises M0B
The four containment properties at 100% over 20 trials on real boundaries; W1 log on the pinned configuration; ER-1…ER-13 done; restore test passed.
G2 → authorises M1
Safety: every deterministic gate, Q-8 = 0. Value: Q-1, Q-2, Q-4 meet targets; Q-3, Q-5–Q-7 in ceilings; operator holds a value veto.
Plan §7, §7.1 charter, §7.2 gates · critical path G0 → W3 → W4 → W7 → W8 = 28 eng-days
9

## Slide 10
Status: M0 code drafted ahead of G0
Development evidence only: one uid, file anchor store, fake observer and provider
106
tests passing
14
skipped: need pinned runtime / live key
6.8k
lines of Python (valops/)
14
degraded-mode runbooks
Code exists (dev evidence)
W2
W3
W4
W5
W6
W6b
W7
W9
W10
W11
W12
W13
W14
W15
W16
W17
W19
W21
W22
W23
Not started: needs G0, pins, real hosts or live models
W0
G0 package
W1
Claude pin
W1-O
Codex
W1-G
Antigravity
W8
real-boundary
W24
PA runs
W20
baseline
W18
run-in
Also not built
Watchtower notification ingestion (the sentinel only checks a heartbeat file)
Offline hardware-token signing (D14) wired into the valops bundle CLI
Real runs of the S3 object-lock anchor and the ops ↔ validator mTLS link (both implemented)
docs/IMPLEMENTATION-NOTES.md §1, §3 · pytest -q on 2026-09-21: 106 passed, 14 skipped in 100 s
10

## Slide 11
Gate readiness
All three gate records (docs/gates/G0–G2.md) read “pending”
G0
Pending
10 G0-due decisions open, all with proposed defaults: D1, D3, D5, D6, D7, D11, D14, D15, D16, D19
7 register parameters still null (P-02, P-03, P-06, P-07, P-16, P-28, P-30); the bundle builder refuses to build
Version, identity and price placeholders (REPLACE_AT_*) in the bundle source
DRIs, security reviewer and operator not named
G1
Blocked on G0
W1: SDK options not yet run on a pinned SDK
failIfUnavailable discrepancy unresolved; fail-closed currently comes from the bwrap pre-flight
No real-boundary runs: separate uids, WORM anchor, mTLS link, real keys
ER-1 … ER-13 not signed off; no restore test
G2
Not started
Judge adversarial, diagnosis quality and operator-value suites need a live model and the testnet validator
Fixtures and Wilson statistics exist (eval/)
Watchtower baseline campaign, then the 28-day run-in
docs/registers/decisions.yaml, parameters.yaml · policy/bundle-src · IMPLEMENTATION-NOTES §3
11

## Slide 12
What the build taught the design
17 deviations (N-1 … N-17) found in coding, now reconciled into HLD v0.5 §14.3. Highlights:
ID | Change | Why
N-1 / N-2 | Store grows from 3 to 5 endpoints | A separate socket per broker keeps the socket as the principal; tool-driven re-samples become citable signals
N-3 | Sockets bind-mounted, not inherited | SO_PEERCRED is captured at connect(); an inherited fd would carry the controller's identity
N-4 | Judge retries exhausted → handed_off | The safer of two conflicting readings; §7.2 now agrees with R-3, §9 and RB-2
N-7 | Store rejects mode-specific advice under unknown | A deterministic layer in front of a model-quality control
N-8 | Alert fields filled from the record | A persuaded reporter can't misstate the verdict or severity
N-10 / N-12 | No refusal fallback; conservative metering | Keeps the pinned model; limits still bind when usage can't be parsed
docs/IMPLEMENTATION-NOTES.md §2 · HLD §14.3
12

## Slide 13
Key risks and kill criteria
Risks → mitigations
W1 invalidates the SDK sandbox or permission model
Main schedule risk. Close the gap outside the SDK, or stop (kill 1)
A runtime ships built-in tools it can't remove
PC-2 inertness under a minimal rootfs, or native-only admission
Worker compromise via prompt injection
Scoped short-lived token; brokers re-check everything; no key, no write
Observation degrades the validator
cgroup limits, concurrency 1, rate caps, RPC breaker; Q-7 measured
M0 builds something the operator won't use
Watchtower baseline; the operator holds a value veto at G2
Stop if…
SDK semantics can't guarantee SR-3/4/10/11 and the gap can't be closed outside the SDK
M0A can't show its 4 properties, even after one extension of half the time box
Any unauthorised execution not traceable to a fixable defect
The Judge misses any seeded case (M0 tolerance: zero)
Operator-value evidence doesn't support the hypothesis. Passing safety gates isn't a reason to continue
Plan §10, §12 · §7.1 schedule note
13

## Slide 14
Decisions needed to move
1
Approve the G0 package
Close or adopt defaults for D1, D3, D5, D6, D7, D11, D14, D15, D16, D19. Name the DRIs, the independent security reviewer, the operator + backup and the injector.
2
Pin and verify the reference configuration
Pin the Python + claude-agent-sdk + model ID (D7), then run W1 and resolve failIfUnavailable.
3
Stand up real environments
ER-1 … ER-13: testnet validator, hardened ops host, WORM anchor account, key ceremony, mTLS CA, per-class uids.
4
Prove containment → G1
Run the M0A suites on real boundaries, 20 trials at 100%, with a restore test.
5
Staff the provider track
A third engineer for Codex and Antigravity admission (22 eng-days); D21 data terms per provider.